## Group Members
Group Member Name | Role
Hanan f.h. Abutaha | Backend
Sali Ahmed | Team Management & Project Coordination
Mohamed Ayman Mohamed Alfarra | Testing
Wesam Ms Tomizeh | frontend

## Project Overview
Project name | Task Management System
Objective | To develop a web-based system to manage tasks and team collaboration efficiently.
Scope | User registration, login, create tasks, assign tasks, update task status, reporting
Methodology | Agile (Scrum)
Project Duration | 8 Week

## Timeline
Week | Activities
Week 1 | Project planning, requirement gathering, define scope
Week 2 | System analysis and UML design
Week 3 | Database design and backend setup
Week 4 | Backend development (APIs, authentication)
Week 5 | Frontend design and implementation
Week 6 | Integration of frontend and backend
Week 7 | System testing and bug fixing
Week 8 | Final documentation and presentation preparation

## Budget Planning
Resource Type | Description | Estimated Cost ($)
Human Resource | 4 Members - 8 Weeks | 2000
Development Tools | Software tools & hosting | 300
Testing & Documentation | Reports, printing, materials | 100
Total Estimated Budget |  | 2400